# Timeline

| What | Notes |
| --- | --- |
| 8 weeks before course start |  |
| Syllabus Development – map content to weekly modules for the CLE, review learning objectives, calculate time it takes to complete |  |
| Course Design – make blue print for each week, plan pre-recorded lectures and asynchronous work |  |
| 6 weeks before course start |  |
| Syllabus updated -readings, video titles, presentation ppts & assignments |  |
| Pre-record lectures Coordinate video production - Zoom - list video content, people involved - upload to corresponding box folder - coordinate close captioning for videos that are to be used more than one term |  |

| 1 month before course start date |  |
| --- | --- |
| Review and finalize course policies including: learner’s contract, grading, weekly and final evaluations |  |
| Update Course site Final syllabus review/course revisions |  |
| Tas/Group leaders recruited |  |
| 2 weeks before course start date |  |
| Complete all pre-recorded lectures |  |
| Welcome videos of faculty, Intro to the course |  |
| TA/Group leader orientation |  |
| Welcome Letter to Students |  |
| Schedule of Assignments/Calendar distributed |  |
| Student orientation/Sync sessions/office hours scheduled |  |
| Review Course site |  |
| 2 weeks after course end date |  |
| Course de-brief Student evaluations reviewed |  |